## BASE BID
|  | SCOPE : | Electrical
|  | PROJECT LOCATION : | Two-Storey Suite-24 Toye Street, Red Deer, AB
|  | DATE SUBMITTED : | 2025-03-09
|  | PROJECT TYPE: | Private
|  | REVISION NO.: | 00
ITEM # | CSI DIV. | DESCRIPTION | BARE QTY. | WASTAGE | QTY. WITH WASTAGE | UNIT | UNIT LABOR HOURS | TOTAL LABOR HOURS | PER HOUR LABOR RATE | TOTAL LABOR COST | UNIT MATERIAL COST | TOTAL MATERIAL COST | ITEM COST | TRADE COST
| 01 00 | GENERAL REQUIREMENTS | [11 empty] | 32883.84
1 |  | Plan Design & Permitting | 1 | 0% | 1 | LS | 94.032 | 94.032 | 40 | 3761.28 |  | 0 | 3761.28
2 |  | Utilities | 1 | 0% | 1 | LS | 158.976 | 158.976 | 40 | 6359.04 |  | 0 | 6359.04
3 |  | Equipment & Tools | 1 | 0% | 1 | LS | 84.96 | 84.96 | 40 | 3398.4 |  | 0 | 3398.4
4 |  | Signage & Promotion | 1 | 0% | 1 | LS | 93.6 | 93.6 | 40 | 3744 |  | 0 | 3744
5 |  | Cleaning & Final | 1 | 0% | 1 | LS | 70.272 | 70.272 | 40 | 2810.88 |  | 0 | 2810.88
6 |  | Bonds, Insurance, Legal | 1 | 0% | 1 | LS | 43.2 | 43.2 | 40 | 1728 |  | 0 | 1728
7 |  | Project Management & Supervision | 1 | 0% | 1 | LS | 277.056 | 277.056 | 40 | 11082.24 |  | 0 | 11082.24
| 26 00 | ELECTRICAL | [11 empty] | 55427.11
LIGHTING FIXTURES
8 |  | Linear Lighting Fixture | 6.54 | 5% | 7 | LF | 0.3 | 2.1 | 60 | 126 | 40.85 | 285.95 | 411.95
9 |  | 1'X4' Stair Lighting Fixture | 8 | 0% | 8 | EA | 1.4 | 11.2 | 60 | 672 | 175 | 1400 | 2072
10 |  | 6" Dia Pendant Light | 1 | 0% | 1 | EA | 1.5 | 1.5 | 60 | 90 | 182 | 182 | 272
11 |  | 6" Dia Recessed Downlight | 44 | 0% | 44 | EA | 1 | 44 | 60 | 2640 | 165 | 7260 | 9900
12 |  | Ceiling Fan W/Light | 6 | 0% | 6 | EA | 2 | 12 | 60 | 720 | 336 | 2016 | 2736
13 |  | Vanity Lighting Fixture | 4 | 0% | 4 | EA | 1.25 | 5 | 60 | 300 | 185 | 740 | 1040
14 |  | Wall Mounted Lighting Fixture | 27 | 0% | 27 | EA | 1.5 | 40.5 | 60 | 2430 | 176 | 4752 | 7182
15 |  | Ceiling Mounted Lighting Fixture | 2 | 0% | 2 | EA | 1 | 2 | 60 | 120 | 165 | 330 | 450
16 |  | Exterior Wall Sconce Lighting Fixture | 18 | 0% | 18 | EA | 1.5 | 27 | 60 | 1620 | 190 | 3420 | 5040
17 |  | Recessed Light, Vapor Proof | 3 | 0% | 3 | EA | 1.2 | 3.6 | 60 | 216 | 168 | 504 | 720
LIGHTING CONTROLS
18 |  | 3-Pole Lighting Control Switch | 2 | 0% | 2 | EA | 1 | 2 | 60 | 120 | 48 | 96 | 216
19 |  | Single Pole Lighting Control Switch | 33 | 0% | 33 | EA | 0.6 | 19.8 | 60 | 1188 | 22 | 726 | 1914
POWER ITEMS
RECEPTACLES
20 |  | Duplex Receptacle | 52 | 0% | 52 | EA | 0.55 | 28.6 | 60 | 1716 | 15 | 780 | 2496
21 |  | Duplex Receptacle, Ground Fault Circuit Interrupter | 34 | 0% | 34 | EA | 0.296 | 10.064 | 60 | 603.84 | 50 | 1700 | 2303.84
22 |  | Duplex Receptacle, Ground Fault Circuit Interrupter, Weather Proof | 16 | 0% | 16 | EA | 0.296 | 4.736 | 60 | 284.16 | 65 | 1040 | 1324.16
23 |  | 220V Receptacle For Boiler, 15-30R | 1 | 0% | 1 | EA | 0.9 | 0.9 | 60 | 54 | 32 | 32 | 86
24 |  | 220V Receptacle For Range, 15-60R | 2 | 0% | 2 | EA | 0.9 | 1.8 | 60 | 108 | 32 | 64 | 172
25 |  | 220V Receptacle For Washing/Dryer, 15-30R | 2 | 0% | 2 | EA | 0.9 | 1.8 | 60 | 108 | 32 | 64 | 172
SWITCHES
26 |  | 2-Pole Disconnect Switch | 1 | 0% | 1 | EA | 0.56 | 0.56 | 60 | 33.6 | 200 | 200 | 233.6
27 |  | 400A 2P Main Disconnect Switch, Assumed Rating | 1 | 0% | 1 | EA | 3.85 | 3.85 | 60 | 231 | 485 | 485 | 716
28 |  | 40A, 2P Non Fused Disconnect Switch For Ahu | 1 | 0% | 1 | EA | 0.64 | 0.64 | 60 | 38.4 | 64 | 64 | 102.4
29 |  | Single Pole Disconnect Switch | 2 | 0% | 2 | EA | 1.5 | 3 | 60 | 180 | 180 | 360 | 540
PANELS
30 |  | Electrical Panel, 120/240v, 1-Phase, 3-Wires, Main Bus: 100A, Main Type: 100A Mcb | 2 | 0% | 2 | EA | 0 | 0 | 60 | 0 | 0 | 0 | 0
ELECTRICAL METER
31 |  | 200A Electrical Meter Socket | 2 | 0% | 2 | EA | 0 | 0 | 60 | 0 | 0 | 0 | 0
DETECTORS
32 |  | Smoke Detector (Ceiling Mounted) | 8 | 0% | 8 | EA | 1.5 | 12 | 60 | 720 | 280 | 2240 | 2960
LOW VOLTAGE COMMUNICATION OUTLET
33 |  | Wall Mounted Tv Outlet/Jack | 7 | 0% | 7 | EA | 1 | 7 | 60 | 420 | 95 | 665 | 1085
MISCELLANEOUS
34 |  | Wall Mounted Junction Box For Ev, If Need (Location: Garage) | 4 | 0% | 4 | EA | 1 | 4 | 60 | 240 | 54 | 216 | 456
WIRING FOR LIGHTING ITEMS
35 |  | 14/2 Nmd Cable For Lighting (Residential Wire) | 1310 | 5% | 1376 | LF | 0 | 0 | 60 | 0 | 0 | 0 | 0
WIRING & CONDUIT FOR POWER ITEMS
36 |  | 14/2 Nmd 90 Cable For Receptacle | 2005 | 5% | 2106 | LF |  | 0 | 60 | 0 |  | 0 | 0
37 |  | 12/2 Nmd 90 Cable For Kitchen Receptacles | 280 | 5% | 294 | LF |  | 0 | 60 | 0 |  | 0 | 0
37 |  | 12/3 Nmd 90 Cable For Equipment | 20 | 5% | 21 | LF |  | 0 | 60 | 0 |  | 0 | 0
38 |  | 10/3 Nmd 90 Cable For Ac/Dryer | 180 | 5% | 189 | LF |  | 0 | 60 | 0 |  | 0 | 0
39 |  | 8/3 Nmd 90 Cable For Ev Charger | 205 | 5% | 216 | LF |  | 0 | 60 | 0 |  | 0 | 0
40 |  | 8/3 Nmd 90 Cable For Stove | 70 | 5% | 74 | LF |  | 0 | 60 | 0 |  | 0 | 0
41 |  | 3#3 kcmil Alu Usei Cable For Panel | 60 | 5% | 63 | LF |  | 0 | 60 | 0 |  | 0 | 0
42 |  | 3#250 kcmil Alu Usei Cable For Main | 40 | 5% | 42 | LF |  | 0 | 60 | 0 |  | 0 | 0
LOW VOLTAGE CABLING
41 |  | 2#14 Fplr Cable For Smoke Detector | 90 | 5% | 95 | LF | 0.12 | 11.4 | 60 | 684 | 1.24 | 117.8 | 801.8
43 |  | Rg6 Cable For Tv Outlet | 285 | 5% | 300 | LF | 0.2 | 60 | 60 | 3600 | 1.4 | 420 | 4020
CONDUIT
44 |  | (19 mm Dia.) Conduit Conduit Material is EMT | 375 | 5% | 394 | LF | 0.154 | 60.676 | 60 | 3640.56 | 2.7 | 1063.8 | 4704.36
45 |  | Allowance for Electrical Items and Installation of Conduit (Hangers, Briddle Rings, J-Hooks) - (3412 SF) | 1 | 0% | 1 | LS | 5 | 5 | 60 | 300 | 1000 | 1000 | 1300
SUB TOTAL | [7 empty] | 1208.822 |  | 56087.4 |  | 32223.55 | 88310.95 | 88310.95
|  | GENERAL REQUIREMENTS | 01 00
|  | SITE CONDITIONS | 02 00
|  | CONCRETE | 03 00
|  | MASONRY | 04 00
|  | METAL | 05 00
|  | WOOD, PLASTICS & COMPOSITES | 06 00
|  | WATERPROOFING | 07 00
|  | OPENNINGS | 08 00
|  | FINISHES | 09 00
|  | SPECIALITES | 10 00
|  | EQUIPMENT | 11 00
|  | FURNISHINGS | 12 00
|  | SPECIAL CONSTRUCTION | 13 00
|  | CONVEYING EQUIPMENTS | 14 00
|  | FIRE SUPPRESSION | 21 00
|  | PLUMBING | 22 00
|  | HVAC | 23 00
|  | INTEGRATED AUTOMATION | 25 00
|  | ELECTRICAL | 26 00
|  | COMMUNICATIONS | 27 00
|  | ELECTRONIC SAFETY AND SECURITY | 28 00
|  | EARTHWORK | 31 00
|  | EXTERIOR IMPROVEMENT | 32 00
|  | UTILITIES | 33 00

## SUMMARY
|  | SCOPE : | Electrical
|  | PROJECT LOCATION : | Two-Storey Suite-24 Toye Street, Red Deer, AB
|  | DATE SUBMITTED : | 2025-03-09
|  | PROJECT TYPE: | Private
|  | REVISION NO.: | 00
ITEM # | CSI DIV. | DESCRIPTION |  | TOTAL LABOR COST | TOTAL MATERIAL COST | TRADE COST
| 01 00 | GENERAL REQUIREMENTS |  | 32883.84 | 0 | 32883.84
| 26 00 | ELECTRICAL |  | 23203.56 | 32223.55 | 55427.11
SUB TOTAL |  |  |  | 56087.4 | 32223.55 | 88310.95
MATERIAL TAX |  |  | 8.25% | 0 | 2658.4429 | 2658.4429
OVERHEAD & PROFIT / INFLATION (Material) |  |  | 10% | 0 | 3222.355 | 3222.355
OVERHEAD & PROFIT (Labor) |  |  | 15% | 8413.11 | 0 | 8413.11
BOND FEE |  |  | 1.5% |  |  | 1539.0729
TOTAL BASE BID | [5 empty] | 104143.9307
| Note |  |  | Legend
1 | The drawings are scaled as per the mentioned scale on the provided drawings. |  |  | DIV. = Division
2 | The prices used above are standard prices unless otherwise noted. |  |  | F.C = Waste or diff. factor
D.O. = Daily Output
| Exclusions |  |  | LBR. HR. = Labor Hours
1 | Union Wages. |  |  | M = months
2 | Any work not mentioned above. |  |  | SM = square meter
3 | Building Charges (if any). |  |  | M = meter
4 | Security fee (if any). |  |  | EA = each
CM = cubic meter
SY = square yard
LOC = location
LS = lump sum
LBS = pounds
|  | GENERAL REQUIREMENTS | 01 00
|  | SITE CONDITIONS | 02 00
|  | CONCRETE | 03 00
|  | MASONRY | 04 00
|  | METAL | 05 00
|  | WOOD, PLASTICS & COMPOSITES | 06 00
|  | WATERPROOFING | 07 00
|  | OPENNINGS | 08 00
|  | FINISHES | 09 00
|  | SPECIALITES | 10 00
|  | EQUIPMENT | 11 00
|  | FURNISHINGS | 12 00
|  | SPECIAL CONSTRUCTION | 13 00
|  | CONVEYING EQUIPMENTS | 14 00
|  | FIRE SUPPRESSION | 21 00
|  | PLUMBING | 22 00
|  | HVAC | 23 00
|  | INTEGRATED AUTOMATION | 25 00
|  | ELECTRICAL | 26 00
|  | COMMUNICATIONS | 27 00
|  | ELECTRONIC SAFETY AND SECURITY | 28 00
|  | EARTHWORK | 31 00
|  | EXTERIOR IMPROVEMENT | 32 00
|  | UTILITIES | 33 00